## Slide 1: Week 3
Project Management

## Slide 2: Agenda
[15 min] General Q&A
[3 x 15min] Team Presentations: Requirements
[1 hour] Lecture: Project Management (text Ch. 3, 12, 13, 14)
[3 x 15min] Team meetings
Next week:
  Project plan & process docs – artifacts & presentations
  Lecture: high level design
  Team meetings

## Slide 3: Overview
Project management (generally) – roles, task deconstruction
Tools – Gantt charts, Kanban boards
Lifecycle variations
Tracking & risk management

## Slide 4: Roles (non-technical)
Executive sponsor – budget, air cover
Customer stakeholders – define requirements, acceptance testing
Project manager – plan, track, mitigate risk, communicate status
  Technical skills – perhaps a former developer
  Organizational (& clerical) skills
  People skills – interface between tech & non-tech audiences
Customer liaison – sometimes the project manager
QA process analyst – studies / measures & helps refine the process

## Slide 5: Project planning in the abstract
Is similar in some ways to system design...
Can be performed at high & low levels
  Rough blocking – major milestones?
  What can generally get done in the allotted timebox?
  Fill in details later
Lots of moving parts, dependencies – some maybe outside your control!
Can / should be agile / iterative – agile does not mean no plan!
  Plans should be reviewed with stakeholders, incl. & especially the tech team
You will often be asked to plan based on insufficient data!
  You will often be asked to commit to delivery based on a high-level plan!
A plan usually doesn't survive first contact with the enemy
  And the enemy R us! Revisit often, update planning artifacts
Track your estimation accuracy... how can it improve?

## Slide 6: Typical project tasks Some things/aspects to think about, make time for
Requirements management
Project planning – schedule & cost the work
Quality assurance – monitor the engineering process (e.g. testing got done)
Configuration management – of the software source, docs, deployment
Organizational process focus – org quality awareness, introspection
Training – to perform roles on the team, for technology adoption
Peer review – of all requirements, designs, docs, code
Design
Implementation
Test – internal, external, reviews (e.g. security audit)
Release / Operational handoffs

## Slide 7: Gantt Charts
Show tasks in time – estimated in duration, start / end time
    How many hours per working day? How many working days per month?
    What are the units on estimates? How accurate & precise are we / can we be?
Show dependencies between tasks – illustrate "critical path" - minimum time needed to complete all tasks
Assign to resources (persons & other)
Multiple views:
  Task view
  Resource-specific view
Some tracking tools will produce Gantt
  nice to not maintain the data in two places!
As tasks are completed, Gantt can show tracking of project actual vs. Plan
  Show % complete
Fibs sequence?

## Slide 8: Project planning in the details – Gantt charts

## Slide 9: Kanban boards
From Toyota
Principles
  Visualize your work
  Limit your work in process
  Focus on optimizing flow: work "in progress" = capacity of system
  Practice continuous improvement
Formerly implemented with actual cards / sticky notes on a wall
Numerous digital versions exist
Multiple views – macro (project view), micro (per iteration view)

## Slide 10
Iteration
View

## Slide 11
Iteration
View

## Slide 12: Bug tracking
Project tasks can be planned or discovered
Defects / bugs can (& should) be tracked in the same tool
  Reviewed, prioritized, scheduled, assigned
Ideally customers would have a mechanism to report defects
  Subject again to review before action

## Slide 13: Project (& Iteration?) Planning: Lifecycle variations (1)
Predictive models: we assume we know things up front
  Clear customer vision & sponsorship
  Manageable & realistic scope
  Experienced development team & leadership
  Using established technologies, established processes ("rinse & repeat" jobs)
  Common in physical engineering... we don't usually build a bridge "experimentally"
Adaptive models: assume we don't know everything up front... that information, priorities & goals can & do change
  Ambiguous or evolving requirements
  Limited resources
  Experimental prototyping

## Slide 14: Lifecycle variations (2) Predictive
Waterfall – all requirements gathering & major design up front
  Feedback allowed if defects in upstream artifacts discovered
  Can be circular – maintenance loops back to (more) requirements
  Sashimi variation – phases overlap slightly
Can also use "mini-waterfall" as a framework for the steps which occur during one iteration of a larger effort

## Slide 15: Lifecycle variations (3) Adaptive
Agile – iterate on MVPs (minimum viable product)
  Does not mean there is no plan nor an overarching design – it means we agree to adopt those plans & designs provisionally until proven, else adapt
In each iteration, we do
"just enough":
Requirements
Design
Implementation
Test
Deploy
We admit we don't know everything up front!

## Slide 16: Agile Manifesto http://agilemanifesto.org/principles.html
Early & continuous product delivery, short iterations
Embrace change
Small, sustainable, motivated teams working together daily
  "Face-to-face" (though video chatrooms can work too...)
  Adaptable
  Self-reflective
  Self-organizing
Technical excellence & attention to detail; focus on quality
Document "just-in-time" & "good enough", doc != product
Success = working product

## Slide 17: Scrum (1)
One application of agile principles
Roles
  Product owner – writes user stories, plans releases, communicates status
  Scrum master – runs daily meetings, clears obstacles to executing the plan
  Team members – self-organizing, perform design, implementation, test, etc.
Time divided into iterations aka sprints of 1 to 4 weeks in length
  Goal of the timebox is a shipped product / new feature(s)
Sprint starts with planning – whole team is involved in stocking the sprint & committing to the objective
  Tasks are estimated with the Fibonacci sequence & added to the sprint
  What is the capacity of the team? Are all team members created equal?

## Slide 18: Scrum (2)
Daily project tracking (15-minute stand-up meeting)
  What was accomplished since last stand-up?
  What will be accomplished before the next stand-up?
  What obstacles need clearing to accomplish the goal?
Progress is tracked in the tracking tool & burndown measured
  Will we meet the objectives at this rate of progress?
Sprint ends with reflective meeting – what went well / not well?
  Actual performance is used to drive the estimation in the next sprint
  Did we over-estimate our capacity? Under-estimate specific tasks?
  See www.scrum.org - get certified!

## Slide 19: Feature delivery: Predictive, Iterative, Incremental, Agile
"Fidelity" - how "complete" is a given feature?
  Low fi – a thumbnail or limited functionality implementation
  Hi fi – fully realized / full featured
Predictive: all is known up-front = all features at same time at high fi
Iterative: provide all features at low fi, then iterate increasing fidelity
Incremental: minimum number of features, but each at high fi
Agile: provide fewest possible features at low fi (MVP!)

## Slide 21: Pros & Cons
Of predictive
Of adaptive
Homework: For discussion in opening Q&A next week (see chapters 12 & 13)

## Slide 22: Project Tracking Needs doing no matter what the SDLC model
Tracking frequency is a matter of some debate...
  Some like daily stand-ups, some prefer less frequent
  Sometimes it’s a meeting, sometimes it’s a walk-around / Skype-around
  Sometimes time zones are a factor
  Face-to-face vs. video vs. status reports
Tracking tool of choice should be the single source of truth for status
Team members can update status in the tool & avoid inquisitions
Large teams: "scrum of scrums" rollup status / rolldown planning
See Scott Ambler "Scaled Agile":
https://pdfs.semanticscholar.org/5fba/5b24d01bfb4956232e82b1129b7bd07f783a.pdf

## Slide 23: Risk Management – rules of thumb (1)
Break work into small tasks – estimates are more likely to be accurate
No task > (5, 8, 13) days, if so, decompose
Fibonacci sequence estimation – 1, 2, 3, 5, 8, (13, …)
Frequent status checks – catch drift from schedule early
Expect the unexpected – pad estimates to account for error (25% to start?)
Insist on peer review of important project artifacts – catch defects early
Assign the right task to the right resource
  Budget for training, pad estimates of new resources accordingly
  Don’t continuously overload the same people... make effort to build a team
  Promote a culture of keeping it real - who needs fake project plans & status theater...

## Slide 24: Risk Management – rules of thumb (2)
Don't overpromise – under-promise, over-deliver
Don't over-engineer – don't build a Cadillac when a Yugo will suffice
Rank requirements / features by complexity
  Will it require some new technology? Might the new technology not work?
Get good at workarounds (watch MacGyver...)
Review the project plan – are their critical tasks which if they slip / fail there could be broad ramifications?
  Should we apply extra resources / attention to this task?
Assess your executive sponsorship
  How important is the project to management? Is it properly funded? Clear vision?
Be realistic!
Web time!

## Slide 25: More project management maxims (1)
The right project management technique / lifecycle model depends on the organization
  Bank? Military? Garage start-up?
  Rarely is the textbook process applied as-is
  Most project management / tracking tools are customizable enough to bend to the particulars of an organization
A happy team mitigates project risk (turnover is disruptive)
Hire good people, train them, let them work
Get over trying to be in control – learn to surf the chaos, exert influence
Big bang integrations almost never work
  Iterate the integration of components into the finished system even when using waterfall!
  Strive to "integrate continuously" (CI / (CQ) / CD tooling)

## Slide 26: More project management maxims (2)
The prototype almost always becomes the product
  Build in quality from the start, in small feature increments
  Set reasonable expectations for delivery with management
  Be careful of accumulating "technical debt" from hacking demos
Three most important aspects (according to Gallo) of the software engineering process
  Requirements management – know what you are building
  Configuration management – manage what you are building
  Peer review – more brains makes better product
Adding staff does not scale productivity linearly
  There is complexity in larger systems of humans
  "Mythical Man Month" - Brooks, 1975 - for discussion next week – pick one maxim from the Brooks book (Wikipedia...)

## Slide 27: Scrappy Project Management More maxims...
Scrappy Project Checklist
https://scrappyprojectmanagement.com/wp-content/uploads/2015/04/Scrappy-Project-Management-Checklist.pdf
For next week – read & discuss
See also:
https://www.ted.com/talks/simon_sinek_how_great_leaders_inspire_action
https://www.ted.com/talks/simon_sinek_why_good_leaders_make_you_feel_safe
For a minute forget how or what... Why? why do we exist as a company / team / product?